## Q2
| Activity | Predecessors | Activity Time | Early start | Early Finish
A | Develop conference theme |  | 3 | 0 | 3 | Project Finish Time | 68
B | Determine attendees 3 |  | 3 | 0 | 3
C | Contract facility | A | 7 | 3 | 10
D | Choose entertainment | A | 10 | 3 | 13
E | Send announcement | B | 5 | 3 | 8
F | Order gifts | B | 5 | 3 | 8
G | Order materials | B | 1 | 3 | 4
H | Plan schedule of sessions | C | 40 | 10 | 50
I | Design printed materials | B,H | 15 | 50 | 65
J | Schedule session rooms | C | 1 | 10 | 11
K | Print directions | H | 10 | 50 | 60
L | Develop travel memo | E | 5 | 8 | 13
M | Write gift letter | F | 5 | 8 | 13
N | Confirm catering | H | 3 | 50 | 53
O | Communicate with speakers | H | 3 | 50 | 53
P | Track RSVPs and assign roommates | L | 30 | 13 | 43
Q | Print materials | I | 3 | 65 | 68
R | Assign table numbers | P | 1 | 43 | 44
S | Compile packets of materials | G | 3 | 4 | 7
T | Submit audio-visual needs | O | 1 | 53 | 54
U | Put together welcome letter | P | 5 | 43 | 48
V | Confirm arrangements with hotel | P | 3 | 43 | 46
W | Print badges | G,P | 7 | 43 | 50

## Q3
|  | number of cancellation | number of cancellation( fix) | number of overbooking | overbooking cost | profit
unit charge | 300 | 20 | 15 | 22 | 2750 | 34750
overbooking cost | 125 | 17 | 1 | 36 | 4500 | 33000
|  | 3 | 4 | 33 | 4125 | 33375
|  | 13 | 19 | 18 | 2250 | 35250
|  | 3 | 19 | 18 | 2250 | 35250
|  | 3 | 14 | 23 | 2875 | 34625
|  | 10 | 9 | 28 | 3500 | 34000
|  | 14 | 17 | 20 | 2500 | 35000
|  | 13 | 1 | 36 | 4500 | 33000
|  | 8 | 13 | 24 | 3000 | 34500
|  | 3 | 10 | 27 | 3375 | 34125
|  | 10 | 1 | 36 | 4500 | 33000
|  | 7 | 3 | 34 | 4250 | 33250
|  | 17 | 10 | 27 | 3375 | 34125
|  | 2 | 12 | 25 | 3125 | 34375
|  | 2 | 13 | 24 | 3000 | 34500
|  | 1 | 20 | 17 | 2125 | 35375
|  | 2 | 4 | 33 | 4125 | 33375
|  | 7 | 16 | 21 | 2625 | 34875
|  | 3 | 17 | 20 | 2500 | 35000

## Q4
| Input | Input | Input | input | output | output | output | output | output |  | Input | Input | Input | input | output | output | output | output | output
| Cost to manufacture | Cost to outsource | Capital | Demand | Manufacture cost | outsourcing cost | Decision | Decision (0,1) | Cost difference |  | Cost to manufacture | Cost to outsource | Capital | Demand | Manufacture cost | outsourcing cost | Decision | Decision (0,1) | Cost difference |  |  | Manufacturing less than 90%max | Manufacturing less than 85%max
Trail | 125 | 172 | 50010 | 915 | 164385 | 157380 | outsource | 1 | -7005 | Trail | 125 | 172 | 50010 | 915 | 164385 | 157380 | outsource | 1 | -7005 | 90% max of Manufacture cost | 170040.9411
1 | 123.2306 | 182.1681 | 47300 | 897 | 157837.8744 | 163404.8016 | Manufacture | 0 | 5566.9272 | 1 | 86.6773 | 180.9238 | 47300 | 943 | 129036.7338 | 170611.1619 | Manufacture | 0 | 41574.4282 | 85% max of outourcing cost | 161759.4429 | 1 | 0
2 | 127.9221 | 157.4303 | 48440 | 957 | 170861.4406 | 150660.7925 | outsource | 1 | -20200.6481 | 2 | 124.8641 | 184.4629 | 48440 | 835 | 152701.5482 | 154026.5078 | Manufacture | 0 | 1324.9597 |  |  | 1 | 0
3 | 129.8709 | 182.2637 | 50010 | 876 | 163776.8706 | 159662.9582 | outsource | 1 | -4113.9124 | 3 | 139.9412 | 173.3472 | 50010 | 874 | 172318.6269 | 151505.4435 | outsource | 1 | -20813.1834 |  |  | 0 | 0
4 | 115.7588 | 176.4013 | 51600 | 915 | 157519.3171 | 161407.1544 | Manufacture | 0 | 3887.8373 | 4 | 126.7366 | 152.7626 | 51600 | 996 | 177829.6456 | 152151.5924 | outsource | 1 | -25678.0531 |  |  | 0 | 0
5 | 141.465 | 167.7431 | 52500 | 996 | 193399.1691 | 167072.0862 | outsource | 1 | -26327.083 | 5 | 136.6233 | 172.5009 | 52500 | 998 | 188850.0881 | 172155.8712 | outsource | 1 | -16694.2169 |  |  | 0 | 0
6 | 137.5286 | 157.9604 | 47300 | 917 | 173413.7539 | 144849.7056 | outsource | 1 | -28564.0483 | 6 | 143.3546 | 192.6166 | 47300 | 988 | 188934.3791 | 190305.2269 | Manufacture | 0 | 1370.8479 |  |  | 0 | 0
7 | 103.9402 | 182.3217 | 48440 | 901 | 142090.0775 | 164271.8636 | Manufacture | 0 | 22181.7861 | 7 | 119.9998 | 164.6872 | 48440 | 969 | 164719.7722 | 159581.8855 | outsource | 1 | -5137.8867 |  |  | 0 | 0
8 | 120.1284 | 176.0668 | 50010 | 917 | 160167.7107 | 161453.2521 | Manufacture | 0 | 1285.5413 | 8 | 132.486 | 184.8926 | 50010 | 858 | 163682.9864 | 158637.8673 | outsource | 1 | -5045.1191 |  |  | 0 | 0
9 | 130.9399 | 162.8645 | 51600 | 976 | 179397.3546 | 158955.7988 | outsource | 1 | -20441.5558 | 9 | 120.7546 | 197.5336 | 51600 | 859 | 155328.244 | 169681.3901 | Manufacture | 0 | 14353.1461 |  |  | 0 | 0
10 | 126.5289 | 187.611 | 52500 | 852 | 160302.5817 | 159844.6008 | outsource | 1 | -457.9809 | 10 | 127.9004 | 149.6869 | 52500 | 886 | 165819.7946 | 132622.5866 | outsource | 1 | -33197.208 |  |  | 0 | 0
11 | 127.2283 | 172.794 | 47300 | 983 | 172365.4242 | 169856.4865 | outsource | 1 | -2508.9377 | 11 | 114.8692 | 175.3763 | 47300 | 959 | 157459.5443 | 168185.8406 | Manufacture | 0 | 10726.2963 |  |  | 0 | 0
12 | 125.3809 | 165.5885 | 48440 | 950 | 167551.8239 | 157309.0835 | outsource | 1 | -10242.7404 | 12 | 143.9194 | 169.8961 | 48440 | 866 | 173074.1674 | 147130.0416 | outsource | 1 | -25944.1258 |  |  | 0 | 0
13 | 99.5664 | 155.9556 | 50010 | 929 | 142507.1809 | 144882.7516 | Manufacture | 0 | 2375.5707 | 13 | 106.9045 | 150.364 | 50010 | 919 | 148255.2133 | 138184.5272 | outsource | 1 | -10070.6861 |  |  | 0 | 0
14 | 146.8784 | 176.6432 | 51600 | 976 | 194953.3177 | 172403.7622 | outsource | 1 | -22549.5555 | 14 | 129.2795 | 155.8257 | 51600 | 986 | 179069.6074 | 153644.1789 | outsource | 1 | -25425.4285 |  |  | 0 | 0
15 | 130.0234 | 182.0101 | 52500 | 874 | 166140.4627 | 159076.825 | outsource | 1 | -7063.6377 | 15 | 106.0109 | 159.3259 | 52500 | 843 | 141867.1646 | 134311.7081 | outsource | 1 | -7555.4565 |  |  | 0 | 0
16 | 130.8665 | 184.7509 | 47300 | 878 | 162200.8018 | 162211.2688 | Manufacture | 0 | 10.467 | 16 | 129.5568 | 161.0261 | 47300 | 936 | 168565.1598 | 150720.4304 | outsource | 1 | -17844.7294 |  |  | 0 | 0
17 | 115.435 | 180.8436 | 48440 | 994 | 163182.3983 | 179758.5054 | Manufacture | 0 | 16576.1071 | 17 | 127.612 | 193.5498 | 48440 | 963 | 171330.3887 | 186388.4673 | Manufacture | 0 | 15058.0786 |  |  | 0 | 0
18 | 125.8074 | 170.0869 | 50010 | 842 | 155939.8604 | 143213.1778 | outsource | 1 | -12726.6825 | 18 | 123.2226 | 183.4006 | 50010 | 969 | 169412.7117 | 177715.179 | Manufacture | 0 | 8302.4672 |  |  | 0 | 0
19 | 122.439 | 170.4594 | 51600 | 843 | 154816.037 | 143697.2904 | outsource | 1 | -11118.7466 | 19 | 102.8152 | 175.567 | 51600 | 934 | 147629.4374 | 163979.5917 | Manufacture | 0 | 16350.1543 |  |  | 0 | 0
20 | 101.9252 | 157.3755 | 52500 | 985 | 152896.3439 | 155014.882 | Manufacture | 0 | 2118.538 | 20 | 127.3173 | 180.7893 | 52500 | 917 | 169249.9357 | 165783.8309 | outsource | 1 | -3466.1048 |  |  | 0 | 0
[8 empty] | 12 | [9 empty] | 12 |  |  |  | 0 | 0
[22 empty] | 2 | 0
5.6974